## Sheet1
Agile Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Create Job Opportunities | Yes | Yes | High | Complete | 20 | Yes
Forms/GUI for Creating Jobs | Yes | Yes | Medium | Complete | 8 | Yes
Validate Form | Yes | Yes | Medium | Complete | 4 | Yes
Create Tables for Job | Yes | No | Low | Complete | 4 | Yes
Implementing controller for Creating Jobs | Yes | No | Medium | Complete | 4 | Yes
Create Account(Student) | Yes | Yes | Medium | Complete | 24 | Yes
Form for Creating Account | Yes | Yes | Low | Complete | 4 | Yes
Validate Form | Yes | No | Medium | Complete | 8 | Yes
Create tables for student information | Yes | Yes | Low | Complete | 4 | Yes
Implementing controller for account creation | Yes | No | Medium | Complete | 8 | Yes
View Job Opportunities | Yes | No | High | Complete | 12 | Yes
GUI which shows the job opportunities | Yes | No | Low | Complete | 4 | Yes
Implementing controller for retrieving the opportunities from database | Yes | No | High | Complete | 8 | Yes
Apply jobs | Yes | No | Medium | Complete | 28 | Yes
form which allows to apply jobs | Yes | No | Low | Complete | 8 | Yes
Validate Form | Yes | Yes | Medium | Complete | 8 | Yes
create tables for mapping of student to applied jobs | Yes | No | Low | Complete | 4 | Yes
Implementing controller for applying the jobs | Yes | No | Medium | Complete | 8 | Yes
Select Placed Candidates | Yes | No | Low | Not Started | 20 | No
Select the job to display candidates | Yes | No | Low | Not Started | 8 | No
GUI that shows selected candidates | Yes | No | Low | Not Started | 8 | No
Implementing controller to update the database with the selected candidates | Yes | No | Low | Not Started | 12 | No
Generate Reports | Yes | No | High | Complete | 28 | Yes
GUI that have various parameters to generate reports | Yes | No | Medium | Complete | 8 | Yes
create tables which can hold various stats | Yes | No | Medium | Complete | 8 | Yes
Implementing controller for generating reports | Yes | No | High | Complete | 12 | Yes

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started